## How to use
RAID Log
PM Growth Lab ¦ Anzhela Ayvazyan, PMP ¦ pmgrowthlab.com
RAID stands for Risks, Assumptions, Issues and Dependencies. It keeps the four things that most often derail a project in one place, so the whole team looks at the same facts in every status meeting.
How to use it
1 | Risks: things that MIGHT happen. Log them here briefly; use the Risk Register for detailed scoring if your project is large.
2 | Assumptions: things you are treating as true without proof (e.g. 'the vendor will provide test data'). Check each one by a date.
3 | Issues: things that HAVE happened and need action now. Every issue needs an owner and a due date.
4 | Dependencies: work you need from someone else, or that someone else needs from you. Track the date it is needed by.
5 | Walk through the Summary tab at the start of each weekly status meeting, then open the tab with the most red.
6 | When an assumption turns out to be false, or a risk happens, move it to Issues and note where it came from.
Legend
Pale yellow cells: type here.
Grey cells: calculated automatically. Do not overwrite.
Grey italic text in the first rows is an example. Replace it with your own.
Free template from the IT Project Starter Kit: pmgrowthlab.com/starter-kit

## Summary
RAID Summary
Updates automatically from the four tabs. Start every status meeting here.
| Area | Open items | Needs attention | What 'needs attention' means
| Risks | 1 | 0 | High-rated risks still open
| Assumptions | 1 | 0 | Proved wrong, or past their check-by date
| Issues | 1 | 1 | High priority, or past due date
| Dependencies | 1 | 1 | At risk or late
Tip: anything in red gets discussed first. Everything else is a quick 'still on track?' check.

## Risks
RAID Log ¦ Risks
Things that might happen
ID | Risk | Owner | Probability (1-5) | Impact (1-5) | Score | Rating | Mitigation | Status | Review by
R-01 | If the data migration takes longer than planned, then the cut-over weekend is not enough. | Data lead | 3 | 4 | 12 | Medium | Run a full trial migration in week 6 and time it. | Open | 2026-10-26

## Assumptions
RAID Log ¦ Assumptions
Things we are treating as true without proof yet
ID | Assumption | Raised by | Date raised | If it is wrong... | How we will check | Owner | Check by | Status
A-01 | The client's IT team will provide production access by week 3. | Project manager | 2026-10-12 | Deployment testing cannot start; schedule slips. | Confirm in writing at the next steering meeting. | Sponsor | 2026-10-22 | Unchecked

## Issues
RAID Log ¦ Issues
Things that have happened and need action
ID | Issue | Raised | Priority | Owner | Action to resolve | Due | Status | Days open
I-01 | Staging server is down; QA cannot test the sprint build. | 2026-10-10 | High | DevOps lead | Restore from snapshot; raise ticket with hosting provider. | 2026-10-13 | In progress | 2
Formulas:
Days open = IF(OR([Raised]="",[Status]="Resolved"),"",TODAY()-[Raised])

## Dependencies
RAID Log ¦ Dependencies
Work we need from others, or others need from us
ID | Dependency | Direction | From / to (team or vendor) | Owner | Needed by | Status | Notes
D-01 | Single sign-on configuration from the corporate identity team. | Inbound | Corporate IT (identity team) | Tech lead | 2026-11-02 | At risk | Their backlog is full until next month; escalated to IT manager.