## How to use
Risk Register
PM Growth Lab ¦ Anzhela Ayvazyan, PMP ¦ pmgrowthlab.com
A risk is something that has not happened yet but could hurt the project if it does. This register helps you list risks early, score them the same way every time, and agree who acts on each one.
How to use it
1 | Write each risk as 'If [cause], then [effect] on [time, cost, scope or quality]'. Vague risks get vague responses.
2 | Score Probability and Impact from 1 (very low) to 5 (very high). Score and Rating calculate themselves.
3 | Give every risk one named owner, not a team. The owner watches the trigger and runs the response.
4 | Pick a response: Avoid (remove the cause), Mitigate (reduce it), Transfer (e.g. contract or insurance) or Accept (watch it).
5 | Review the register in a short slot every week. Close risks that can no longer happen; add new ones as they appear.
6 | Use the Heat Map tab in steering meetings: it shows where your open risks sit at a glance.
Legend
Pale yellow cells: type here.
Grey cells: calculated automatically. Do not overwrite.
Grey italic text in the first rows is an example. Replace it with your own.
Rating: Score 15 to 25 = High, 8 to 14 = Medium, 1 to 7 = Low.
Free template from the IT Project Starter Kit: pmgrowthlab.com/starter-kit

## Risk Register
Risk Register
Project: [name] Project manager: [name] Last updated: [date]
ID | Risk (If... then...) | Category | Owner | Date raised | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Response actions | Trigger / early warning | Status | Next review
R-001 | If the payment provider's API sandbox is not ready by sprint 3, then integration testing slips and go-live moves by 2+ weeks. | Technical | Lead developer | 2026-10-12 | 3 | 4 | 12 | Medium | Mitigate | Agree sandbox date in writing; build against a mock API in the meantime. | Sandbox date missed or unconfirmed by week 4. | Open | 2026-10-19
R-002 | If key users are not released from daily work for UAT, then defects are found after go-live. | People | Project sponsor | 2026-10-12 | 4 | 3 | 12 | Medium | Avoid | Book UAT days with line managers now; get sponsor to confirm release. | Fewer than 3 testers confirmed 2 weeks before UAT. | Monitoring | 2026-10-26

## Heat Map
Risk Heat Map
Count of OPEN and MONITORING risks by probability and impact. Updates automatically.
| Probability ↓ / Impact → | 1 | 2 | 3 | 4 | 5
| 5 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0 | 1 | 0 | 0
| 3 | 0 | 0 | 0 | 1 | 0
| 2 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0
Totals
| High | 0
| Medium | 2
| Low | 0
| Closed | 0