## How to use
Sprint Planning
PM Growth Lab ¦ Anzhela Ayvazyan, PMP ¦ pmgrowthlab.com
A sprint is a short, fixed period (usually 2 weeks) in which the team commits to a small set of work and finishes it. This workbook helps you work out realistic capacity, pick the right backlog items, and track progress with a burndown chart.
How to use it
1 | Sprint Setup: enter the sprint dates, the sprint goal and each person's available days. Capacity calculates itself.
2 | Write the sprint goal as one sentence describing the outcome, e.g. 'Customers can reset their password without calling support'.
3 | Backlog: list stories in priority order. Estimate in story points (1, 2, 3, 5, 8, 13). Mark Yes in 'In sprint?' for chosen items.
4 | Stop adding items when Committed points reach your Recommended commitment on the Sprint Setup tab.
5 | Update each story's Status during the sprint. Enter remaining points each day on the Burndown tab.
6 | After the sprint, add your completed points to Velocity history. Your recommendation gets more accurate every sprint.
Legend
Pale yellow cells: type here.
Grey cells: calculated automatically. Do not overwrite.
Grey italic text in the first rows is an example. Replace it with your own.
Focus factor: share of time actually spent on sprint work after meetings, support and interruptions (0.6 to 0.8 is typical).
Free template from the IT Project Starter Kit: pmgrowthlab.com/starter-kit

## Sprint Setup
Sprint Setup
Fill in the yellow cells. Everything else calculates.
| Sprint name | Sprint 7
| Start date | 2026-10-12
| End date | 2026-10-23
| Working days in sprint | 10 | Mon to Fri. Adjust for public holidays in the team table.
| Focus hours per day | 6 | Hours a person realistically spends on sprint work.
| Focus factor | 70% | See the How to use tab.
| Sprint goal | Customers can reset their password online without contacting support.
| Team member | Role | Days off this sprint | Available days | Capacity (hours) | Notes
| Sara | Developer | 0 | 10 | 42 | Full sprint
| Omar | Developer | 2 | 8 | 33.6 | Training on day 4-5
| Lina | QA engineer | 0 | 10 | 42
| Daniel | Designer | 1 | 9 | 37.8 | Public holiday
| Team total |  |  | 37 | 155.4
Velocity history (completed points)
| Sprint | Points completed | Available days
| Sprint 4 | 21 | 36
| Sprint 5 | 26 | 40
| Sprint 6 | 24 | 38
Result
| Average points per available day | 0.62281 | From your velocity history.
| Recommended commitment (points) | 23 | Average rate x this sprint's available days.
| Committed so far (points) | 8 | Sum of items marked 'In sprint? = Yes'.
| Headroom (points) | 15 | Negative = over-committed. Remove items.

## Backlog
Product Backlog
Highest priority at the top. Mark the items you commit to this sprint.
Committed points |  | 8
Done points |  | 3
Sprint progress |  | 37.5%
Priority | ID | User story (As a... I want... so that...) | Acceptance criteria | MoSCoW | Points | Owner | In sprint? | Status | Points done
1 | US-101 | As a customer, I want to request a password reset link by email so that I can get back into my account without calling support. | Link sent within 1 minute; expires after 30 minutes; works on mobile. | Must | 5 | Sara | Yes | In progress | 0
2 | US-102 | As a customer, I want clear rules shown while I type a new password so that I set a valid one first time. | Rules visible before submit; error message names the rule that failed. | Must | 3 | Daniel | Yes | Done | 3
3 | US-103 | As a support agent, I want to see when a reset was last requested so that I can answer customer questions. | Timestamp shown on customer profile. | Should | 2 | Omar | No | To do | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Burndown
Sprint Burndown
Enter remaining story points at the end of each day. The chart updates itself.
| Day | Date | Ideal remaining | Actual remaining | Notes
| 0 | 2026-10-12 | 8 | 8
| 1 | 2026-10-13 | 7.2 | 8
| 2 | 2026-10-14 | 6.4 | 8
| 3 | 2026-10-15 | 5.6 | 5
| 4 | 2026-10-16 | 4.8 | 5
| 5 | 2026-10-19 | 4
| 6 | 2026-10-20 | 3.2
| 7 | 2026-10-21 | 2.4
| 8 | 2026-10-22 | 1.6
| 9 | 2026-10-23 | 0.8
| 10 | 2026-10-26 | 0
Day 0 = sprint start. 10 working days = a standard 2-week sprint. Example values in grey italics: replace them.
Formulas:
Date = WORKDAY([Date, row above],1)